## Lexique
SP — Story Points:= Unité de mesure utilisée par l’équipe pour estimer l'effort restant
PO — Product Owner:= Personne responsable de décrire les User Stories + valider
US — User Story:= Description simple d’un besoin utilisateur Chaque US doit avoir : une description claire, des critères d’acceptation, une estimation en SP.
DoD — Definition of Done
Liste d’actions que l’équipe s’engage à réaliser pour considérer un travail terminé.
“Done done”
Validation finale du PO après vérification que :
Product Backlog (PB)
Liste ordonnée de toutes les fonctionnalités et besoins du produit. Il contient : US, bugs, améliorations, tâches techniques.
Le PB est vivant : il change à chaque sprint.
Sprint Planning Phase 1
L’équipe choisit combien de Story Points elle pense pouvoir réaliser au prochain sprint + découpe les US trop grandes.
Sprint Planning Phase 2
L’équipe découpe les US du sprint en tâches techniques et les estime en heures.
Roles Scrum
PO — Product Owner
Responsable du Product Backlog, de la vision produit, de la priorisation, et validation finale des User Stories (“done done”).
Scrum Master
Garant du cadre Scrum, facilite les échanges, enlève les obstacles, aide l’équipe à s’améliorer.
Dev Team / Developers
L'équipe qui construit le produit. Elle est autonome, pluridisciplinaire, et responsable des estimations et de la qualité.
Artefacts Scrum
Product Backlog (PB)
Liste ordonnée de tous les besoins : User Stories, bugs, techniques, améliorations. Évolue en continu.
User Story (US)
Description d’un besoin utilisateur, souvent au format : En tant que… je veux… afin de… Doit avoir des critères d’acceptation.
Criteria of Acceptance (CA)
Tests et conditions que l’US doit satisfaire pour être validée.
Story Points (SP)
Unité d’estimation relative basée sur la complexité, les risques et l’effort. Ce n’est pas du temps.
Sprint Backlog
Ensemble des US sélectionnées pour le sprint + la liste des tâches associées.
Definition of Done (DoD)
Checklist définie par l’équipe pour dire qu’un travail est terminé (tests, QA, review, doc…).
“Done done”
Validation finale par le PO. Le travail est réellement accepté.
Increment
Version du produit potentiellement livrable, produite à la fin du sprint.
Événements Scrum (Events)
Sprint
Cycle time-boxed (souvent 1–4 semaines). À la fin : un incrément utilisable.
Sprint Planning (Phase 1 + Phase 2)
Phase 1 :
Le PO présente les priorités
L’équipe choisit combien de SP elle peut faire
Split des US trop grandes
Phase 2 :
Les US sélectionnées sont découpées en tâches
Estimations en heures
Création du Sprint Backlog
Daily Scrum (Daily Stand-up)
Réunion quotidienne de 15 min :
Ce que j’ai fait
Ce que je vais faire
Obstacles
Sprint Review
Démo du travail terminé, feedback du PO et des parties prenantes.
Sprint Retrospective
Analyse de comment s’améliorer :
Processus
Collaboration
Qualité
Outils
🔹 Pratiques liées (agiles mais pas toujours Scrum “pur”)
Refinement / Grooming
Affiner les US, clarifier, découper, réestimer. Souvent 5–10% du temps du sprint.
MoSCoW (priorisation)
Must have
Should have
Could have
Won’t have now
Velocity
Nombre de Story Points réellement réalisés dans un sprint. Permet d'estimer la capacité future.
Burndown Chart
Graphique montrant les heures ou SP restants dans le sprint.
Release Roadmap
Projection des fonctionnalités livrables par sprint selon la vélocité.
Epic
US trop grande, devra être découpée.
Task / Sub-task
Découpage technique d’une User Story, estimé en heures.
🔹 Principes clés
Time-boxing
Chaque événement a un temps maximal.
Empirisme
Basé sur :
Transparence
Inspection
Adaptation
Auto-organisation
L’équipe choisit comment atteindre l’objectif.
Incrémentalité
Le produit évolue sprint après sprint, version utilisable à chaque fin de cycle.

## Informations
General Information
The Product Backlog total number of SP may vary from sprint to sprint if some US are added or deleted, or if some US are not accepted in a precedent sprint and that they have to be taken again and modified in the next sprint.
It is therefore necessary to manually sum that total of SP at the end of every sprint and update the Release Roadmap
Every day, it is necessary to update the remaining hours estimation related to the tasks of the sprint. That estimation may increase if one thinks that it would take more time than expected.
There is the definition of Done with the list of actions that the team decided to achieve and the definition of done done where the PO has to decide if the done US are ok for him.
Reminder on the work process concerning the PB
1. Description mockup and description of the user acceptance tests by the PO
2. Evaluation of the SP by the team + 30 min / week for re-evaluating it
3. Priorization by the PO (MOSCOW by example or business value, …)
4. Sprint planning phase 1 where the Dev team choose roughly the number of SP that it thinks could be accomplished during the next sprint + split of too big US
5. Sprint planning phase 2 with split in tasks of the current sprint US + estimation in hours
At the bottom of each tab you will find additional information about the objectives of the tab
The Informations tab gives general recommandations about the process to follow in Scrum, especially concerning the way to plan the User Stories with the Product Owner during the Sprint Planning events
Globally you need to have followed a Scrum course to be able to understand this file and the inherent concepts.

## Vision
General information about the project
Project Scope
Centralized issue reporting and management system for mid-size residential buildings, replacing email-based problem tracking.
Tenant Interaction
Tenants submit issues with descriptions, severity, photos, and preferred access windows.
They receive clear, timely status updates (acknowledged, scheduled, waiting for parts, resolved).
Issue Management
Triage and deduplication of reported problems.
Categorization based on keywords, photos, or simple AI suggestions.
SLA tracking with timestamps per status change, varying by issue severity.
Parent-child issue linking for recurring or clustered incidents.
Contractor Coordination
Assign contractors based on availability and SLA requirements.
Track contractor performance (on-time rate, average resolution time, cost per category).
Handle reassignments automatically if jobs are declined or missed.
Schedule visits respecting tenant access windows.
Parts and Costs Management
Track parts source (van inventory vs central store).
Attribute costs to the correct owner.
Analytics & Reporting
Identify recurring issues and patterns by building/unit.
Generate quarterly owner reports: number of incidents, SLA compliance, resolution times, cost breakdown, top root causes.
Privacy & Roles
Tenants see only their unit’s issues.
Owners see only their buildings.
Contractors see only job-relevant details.
Logging of messaging and attachments in context, with optional face-blur for sensitive images.
Operational Features
Triage queue and escalation button for emergencies.
History is immutable; all changes remain visible for audit.
System transparency for tenants through detailed timelines of all actions.
Outcome Goal
Learn from data to improve operations, reduce recurring problems, and provide actionable insights for both management and tenants.
Information
The Vision tab allows the developers to centralize the description of the project, including the general vision, screen copies of the mockups of the different user interfaces , as well as business canvas when appropriate.
Information The Vision tab allows the developers to centralize the description of the project, including the general vision, screen copies of the mockups of the different user interfaces , as well as business canvas when appropriate.

## User Roles
Actor | Rôles | Besoins
OWNERS (Propriétaires d'immeubles) | Possèdent un ou plusieurs immeubles | Rapports trimestriels (coûts, SLA, problèmes récurrents) Vue sur tous leurs immeubles Statistiques de performance
TENANTS (Locataires) | Habitent dans les appartements et signalent les problèmes | Créer des tickets avec photos Proposer des fenêtres d'accès ("dispo après 18h00") Suivre l'état de leurs tickets (transparence) Envoyer des messages
CONTRACTORS (Entrepreneurs/Artisans) | Réparent les problèmes (plombiers, électriciens, etc.) | Recevoir des assignations de tickets Voir les détails nécessaires (accès, pas profil complet du tenant) Décliner ou accepter des jobs Enregistrer le temps de travail et les pièces utilisées
USERS (Managers/Gestionnaires) | Gèrent le système, trient les tickets, assignent les contractors | Trier et catégoriser les tickets (triage queue) Déduplication (3 tenants signalent même problème) Assigner les contractors
Rôles | Personas | Description
End-User | Tenant | Lives in a mid-size residential building; reports issues like leaks, heating problems, or broken fixtures. Needs an intuitive interface to submit issues with photos, select severity, propose access windows, and track status.
Developper | Technical Engineer | Implements the system, manages backend and frontend integration, SLA tracking, issue deduplication, notifications, reporting dashboards, and role-based access. Needs empathy for both tenants and building managers to design useful functionalities.
Marketing | Building Manager | Communicates system benefits to tenants and owners, promotes transparency, ensures adoption, collects feedback on satisfaction, and explains reporting and analytics features to building owners.
Information
In Scrum it is important to understand in details who will use the delivered software in order to develop good and useful functionalities for them.
In this tab we don't just specify that a "User" will use it, we try to be more specific by writting the type of job of that user and even, if possible, the type of persona this user has. In this tab we don't just specify that a "User" will use it, we try to be more specific by writting the type of job of that user and even, if possible, the type of persona this user has.
Like that the developer can use empathy and put himself at the place of that person when developping his or her functionalities.

## ProductBacklog
US Nr. | Theme | As an/a … | I want to … | so that … | Acceptance Criteria | Priority | Status | Story Points | Sprint | US accepted (done done) | MoSCoW
1 | Preparation (Plan) | Developer | Prepare the work environment | Everyone in the team can work without interruptions | Every member of the team has what he needs for work and agree with the used tools | 800 | 3 | 3 | 0 | 2025-12-10 | Must
2 | Preparation (Plan) | Developer | Project design and prototyping | We can have low-fidelity screens and use them as a base throughout development stages. We can use it as the main source of work and keep track of work statuses. | Match with the requirements / user profile | 800 | 2 | 9 | 0 | 2025-12-10 | Must
3 | Preparation (Plan) | Developer | DB Modeling | We can have an understanding of fields that are going to be used and their relations; We can have a visual draft of out DB and what it resembles | The database complies with the vision and meets the stated requirements Match with the requirements / DB modeling | 600 | 3 | 9 | 0 | 2025-12-10 | Must
4 | Research | Developer | Understanding requirement + Vision | We can have a clear vision of what we are trying to do | Everyone okay and undersands what we are going to do and how | 800 | 3 | 6 | 0 | 2025-12-10 | Must
5 | Preparation (Plan) | Developer | Identify roles | We can understand who are going to use our program and how | All roles have been fulfilled and are relevant to the task at hand. | 700 | 3 | 6 | 0 | 2025-12-10 | Must
4 | Preparation (Plan) | Developer | Database modeling initial | We can have an understanding of fields that are going to be used and their relations | The database complies with the vision and meets the stated requirements | 700 | 3 | 6 | 0 | 2025-12-10 | Must
5 | Preparation (Plan) | Developer | Mockup database initial | We can have a visual draft of out DB and what it resembles | Match with the requirements / DB modeling | 500 | 3 | 3 | 0 | 2025-12-10 | Must
6 | Preparation (Plan) | Developer | Mockups and prototypes desingning Initial | We can have low-fidelity screens and use them as a base throughout development stages | Match with the requirements / user profile | 700 | 3 | 6 | 0 | 2025-12-10 | Must
7 | Preparation (Plan) | Team | Create the Product Backlog | We can use it as the main source of work and keep track of work statuses |  | 600 | 1 | 3 | 0 |  | Must
6 | Preparation (Plan) | Team | Vérification requierments | We can set up more clear boundaries and eliminate inaccuracies | The client agreed with proposed solution or he precises what he wants to be changed | 650 | 3 | 1 | 0 | 2025-12-10 | Must
7 | Research | Team | Check Requirements, technologies, objectifs | We can be sure that requirements align with team capacity and mandatory compenents are taken into account |  | 600 | 3 | 1 | 0 | 2025-12-10 | Must
8 | Preparation (Plan) | Developer | Finishing the first DB version structure | We plan and agree on the final tables structure, ids and PK/FK of the whole project. Implement SQL request to Create all table with rights collumn type and restrictions. | All requierement are covered by our DB structure and tables. All tables and columns match with DB structure | 800 | 3 | 18 | 1 | 2025-12-17 | Must
9 | Research | Developer | Research and final choice of the technological stack | All aspects of the project have a defined software/language | All members agree with the chosen technology The technology covering all technical project requiermements | 500 | 3 | 3 | 1 | 2025-12-17 | Must
10 | Preparation (Plan) | Team | Create the Product Backlog (was rejected) | We can use it as the main source of work and keep track of work statuses |  | 600 | 3 | 4 | 1 | 2025-12-17 | Must
11 | Preparation (Plan) | Developer | Mockups and prototypes desingning final | Web interface screens that matches with all wanted functionnality and user's view | Must match the DB structure/logical and include views/fields/functionnality of the project's specifications | 500 | 3 | 6 | 1 | 2025-12-17 | Must
12 | Preparation | Team | Planification of taks and holidays work planning. Preparation for meeting with PO. | How we planned the teamwork (who will do what) and when, during the Winter's Holidays | All Members know what to do , and agreed with the plan | 400 | 3 | 2 | 1 | 2025-12-17 | Could have
13 | Implementation | Developer | Creating all Tables | Implement SQL request to Create all table with rights collumn type and restrictions | All tables and columns match with DB structure | 800 | 3 | 10 | 1 | 2025-12-17 | Must
13 | Implementation | Developer | DB stored procedure and indexing | We can use the database and increase performance | All procedures and indexes are consistent with the DB | 800 | 3 | 5 | 1 | 2025-12-17 | Must
14 | Implementation | Developer | Feed data base with mockup data | We visualize the DB using real world data | All relationships are logical and DB is ready to be used | 600 | 3 | 1 | 1 | 2025-12-17 | Must
15 | Testing | Developer | Testing all Tables , Links (FK) and Columns | All columns contains and accept only the defined values | All table and columns behaves as defined , no errors or wrong values accepted | 600 | 3 | 5 | 1 | 2025-12-17 | Must
16 | Preparation (Plan) | Team | Team technological compatibility check | Сheck with the team how the project is going and mostly if the defined technology is working as expected or if we must adapt something | No core changes in the technological part of the project that may affect a co-worker's tasks | 300 | 3 | 1 | 2 | 2026-01-07 | Could have
17 | Implementation | Developer | Django infrastructure setup | Create the base for application and establish connection with DB so it can be used with backend | Server is accessible and can be connected to; DB entities are represented in backend (ORM) | 900 | 3 | 10 | 2 | 2026-01-07 | Must
22 | Implementation | Developer | Server Django creation | Create the base for application | Server is accessible and can be connected to | 900 | 3 | 4 | 2 | 2026-01-07 | Must
23 | Implementation | Developer | Connection DB and entity creation | So that we can use DB with backend | All entities of the DB are represented in backend (ORM) | 800 | 3 | 6 | 2 | 2026-01-07 | Must
18 | Implementation | Developer | Backend and functions development | Views controller and logics Add functions that will be used between all roles (login, tickets, dashbord, etc.) and specific functions for each role | All functions works from the Python code Layer | 1000 | 2 | 14 | 2 | 2026-01-07 | Must
25 | Implementation | Developer | Implements Python Backend | Views controller and logics | All functions works from the Python code Layer | 900 | 3 | 8 | 2 | 2026-01-07 | Must
26 | Implementation | Developer | Apha-Test | All functionality and data treatment are working as expected | During tests no critical bugs were found | 800 | 3 | 4 | 2 | 2026-01-07 | Must
27 | Implementation | Team | Add minimum PO's requirements | So we have working base of our project | All requirements were fulfilled | 1000 | 3 | 2 | 2 | 2026-01-07 | Must
28 | Implementation | Developer | Add shared functions and views between users | Add functions that will be used between all roles (login, tickets, dashbord, etc.) |  | 900 | 3 | 4 | 2 | 2026-01-07 | Must
29 | Implementation | Developer | Add specific functions and views for each role | Add specific functions which can be used only by corresponding role |  | 800 | 1 | 2 | 2 | 2026-01-07 | Must
19 | Implementation | Tenant | Core issues feature and role-based visibility | Tenants can report problems in their units by filling a form Have access to the information they are authorized to have access | On successful sumbission, issue is created, added to queue and data is saved in database. All statuses exist in the system; each of them is saved in log with timestamp to create history. No access to protected/sensitive information. | 900 | 2 | 10 | 2 | 2026-01-07 | Must
31 | Implementation | Tenant | Issue submission | Tenants can report problems in their units by filling a form. | On successful sumbission, issue is created, added to queue and data is saved in database | 1000 | 3 | 4 | 2 | 2026-01-07 | Must
32 | Implementation | Developer | Issue lifecycle: web interface | We can keep track of issues | All statuses exist in the system; each of them is saved in log with timestamp to create history | 600 | 3 | 2 | 2 | 2026-01-07 | Must
33 | Implementation | Developer | Issue lifecycle: backend | Issues change their status which corresponds to the real job status |  | 900 | 1 |  | 2 |  | Must
34 | Implementation | Developer | Role-Based visilibility | A user with a specific role has access only to the information to which they are authorized to have access | The assigned role may have access to information that the role is authorized to access. No access to protected/sensitive information | 1000 | 3 | 4 | 2 | 2026-01-07 | Must
20 | Testing | Developer | Testing and validation | Сheck with the team how the project is going. All functionality and data treatment are working as expected. | All requirements were fulfilled During tests no critical bugs were found | 800 | 3 | 8 | 2 | 2026-01-07 | Must
36 | Testing | Developer | Beta-Test | All functionality and data treatment are working as expected | During tests no critical bugs were found | 800 | 3 | 2 | 2 | 2026-01-07 | Must
21 | Preparation (Plan) | Team | Add additional PO's requirements | So we have working base of our project | All requirements were fulfilled | 900 | 3 | 2 | 3 | 2026-01-07 | Must
22 | Implementation | Developer | Frontend development using Django Interface | The design and fields match with the mockups. Fields, functionality, login, views are implemented. | Matches the requierements of mockups | 700 | 3 | 16 | 3 | 2026-01-07 | Must
38 | Implementation | Developer | Implement Frontend Web Django Inteface (design) + code-interface | The design and fields match with the mockups | All requirement are included | 500 | 3 | 6 | 3 | 2026-01-07 | Must | Could have
39 | Implementation | Developer | Implement Frontend Web Django Inteface (code-interface) | Fields, functionality, login, views are implemented | Matches the requierements of mockups | 800 | 3 | 10 | 3 | 2026-01-07 | Must | Won’t have now
23 | Implementation | Developer | Implement link between Frontend and Backend | the interface and the python layer are communicating properly | All fields , login request or button are linking properly | 800 | 3 | 8 | 3 | 2026-01-07 | Must
24 | Implementation | Tenant | Simple messaging system and photo upload | All parties can communicate between each other and can attach pictures when reporting issues/using chat | Each issue has it's own messages, where author's name, role and timestamp are shown. Photos can be added upon issue submission or before sending a message/issue | 800 | 3 | 10 | 3 | 2026-01-07 | Must
41 | Implementation | Tenant | Simple messaging system | All parties can communicate between each other | Each issue has it's own messages, where author's name, role and timestamp are shown | 900 | 3 | 6 | 3 | 2026-01-07 | Must
42 | Implementation | Tenant | Upload photos for tickets | Tenants can attach pictures when reporting an issue | Photos can be added upon issue submission or before sending a message | 500 | 3 | 4 | 3 | 2026-01-07 | Must
25 | Implementation | Contractor | Reassignment | In case contractor refuse a job and it has to be reassigned | Contractor can decline a job and then it can be reassigned to another one | 200 | 0 | 8 | 3 |  | Could have
26 | Implementation | Tenant | Extended status model and their visualization with severity awareness (SLA) | Add intermediate statuses/severity levels and visualize all of them for more intuitive understanding | Several levels of severity | 600 | 3 | 4 | 3 | 2026-01-07 | Must
44 | Implementation | Tenant | SLA awareness | So that we can make better decisions about which issues are more important | Several levels of severity | 800 | 3 | 2 | 3 | 2026-01-07 | Must
45 | Implementation | Tenant | Extended status model and their visualization | Add intermediate statuses and visualize all of them for more intuitive understanding |  | 400 | 3 | 2 | 3 | 2026-01-07 | Must
46 | Testing | Developer | Check Security and corrections | The system is secured against extractions or injections | No injection possible , no unwanted access to data | 400 | 0 | 2 | 4 |  | Must
27 | Testing | Developer | Security and final application testing | All functionality and data treatment are working as expected | During tests no critical bugs were found. No injection possible , no unwanted access to data. | 800 | 0 | 14 | 4 |  | Must
28 | Preparation (Plan) | Team | Final check with the client | A final check done with the client before the final product presentation | The client is satisfied | 400 | 0 | 1 | 4 |  | Optional
29 | Preparation (Plan) | Team | Presentation preparation | We can present the result of our project | The client is satisfied and accepts the job that was done | 400 | 0 | 1 | 4 |  | Must
Totaux | [5 empty] | Total SP |  | 186
Note on H2: the priorisation technique MoSCoW: 1.Must have (fundamental feature) 2.Should have (important but short-term workaround available) 3.Could have (can be let out of the realease if time runs out) 4.Won't have this time (later release)
Note on I2: Enter 1, 2 or 3 and the satus is automaticaly displayed (blue = todo, yellow = in progress, green = done and accepted, red= rejected) The task is considered as 'done':3 when all points decided in team are solved (example of done definition : documentation in code, unittests passed, functional tests passed, user manual completed, …)

## Release Roadmap - Velocity
Sprints
| 0 | 1 | 2 | 3 | 4 | 5
Nb SP planned | 44 | 54 | 61 | 70 | 18 | 0
Todo | 35 | 0 | 0 | 0 | 0
Done | 41 | 54 | 59 | 70 | 18
Rejected | 3 | 0 | 2 | 0 | 0
Realized Cum. | 41 | 95 | 154 | 224 | 242
Average |  | 54 | 56.5 | 61 | 60.5
In the table above, replace formulas with real numbers
from the product backlog.
[7 empty] | Blue line | Number of SP for all functionalities to implement
[7 empty] | Green line | Number of Accepted SP
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: - Min 1 US of 1 SP like a Hello World - You should reach the build artifact.
Note on A5: Number of SP at the end of each sprint. That total of SP will change at each sprint
Information
This Tab contains some visual tables and graphs showing how the project is going on. For each sprint we fill the number of total Story Points remaining at the begginning of it, the number of Story Points "done" at the end of the sprint and the number of rejected Story Points.
Then the project velocity graph shows how many User Stories the Team is able to complete per sprint, with a dynamic average. Note that in the initial sprint, when the team has to prepare the working environment, only the "one", Story Point User Story needs to be done. It will be used afterwards to compare with the other User Stories.
The Release Roadmap graph shows the main indicators and allows to quickly answer how many sprint will be necessary to finish all the todos.

## Sprint 0
|  |  | Sprint | 0
| User stories |  | Start date | 2025-12-01
| 1. First time planning and Coordination |  | End date (included) | 2025-12-10
| 6 First contact with PO |  | Sprint goal | Prepare all the environment to be ready to develop the project
| 5 Identify roles |  | Nbre working days | 8
7 Check Requirements, technologies, objectifs
4 Understanding requirement + Vision
2. Project design and Prototyping
2.1 Mockups and prototypes desingning
2.2 Create the Product Backlog
3. DB Modeling
3.1 Database modeling
3.2 Mockup database
4. Setup
1. Prepare the work environment
|  |  | Create the Product Backlog |  | TRAVAIL RESTANT A FAIRE - PAS TRAVAIL DEJA EFFECTUE
[5 empty] | Day 01 | Day 02 | Day 03 | Day 04 | Day 05 | Day 06 | Day 07 | Day 08
ID US.task | Task Name | Resp. | Initial Estimate |  | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-08 | 2025-12-09 | 2025-12-10
1 | Prepare the work environment | Gaëtan | 3 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Mockups and prototypes desingning | Gaëtan | 6 |  | 6 | 5 | 5 | 5 | 3 | 1 | 0.5 | 0
2.2 | Create the Product Backlog | Vadym | 3 |  | 3 | 2 | 2 | 2 | 2 | 0.5 | 0 | 0
3.1 | Database modeling | Gaëtan | 6 |  | 6 | 6 | 5 | 5 | 3.5 | 3.5 | 2 | 2
3.2 | Mockup database | Gaëtan | 3 |  | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
4 | Understanding requirement + Vision | Vadym | 6 |  | 6 | 4 | 2 | 1 | 0 | 0 | 0 | 0
5 | Identify roles | Vadym | 6 |  | 6 | 4 | 3.5 | 1 | 0 | 0 | 0 | 0
6 | First contact with PO | Vadym | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
7 | Check Requirements, technologies, objectifs | Gaëtan | 1 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total | 35
|  | Remaining | 35 |  | 35 | 26 | 18.5 | 15 | 9.5 | 6 | 3.5 | 2
|  | Theoretical |  |  | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0
Note on E5: Modify the table below and Burndown chart according to the number of working days
Note on F17: The first day of the sprint you start at 8 o'clock therefore the remaining effort is the same as the initial estimate
Note on D18: Author: This is the team's initial assessment of how much work is needed to implement this task. The unit is hours. This part must be filled by developers only. Not by the product owner
Note on F18: The first day of the sprint you start at 8 o'clock therefore the remaining effort is the same as the initial estimate
Note on D29: Author: Initial total of Scrum units
Information
This tab contains the sprint backlog, or all the information concerning a specific sprint. We initially set the number of the current sprint, and its goal. Then it contains the list of User Stories chosen by the Team to enter this sprint. We have to modify the different elements like dates, number of working days, number of columns in the table to match with the actual context of the sprint.
The "initial sprint estimation" field contains the number of story points decided to enter this sprint.
Then the team has to split all the User Stories into tasks, add a unique id to each task by following this rule : the initial number corresponds to the ID of the user story, followed by a point, and the second number, which is the number of the task.
When the team will do his daily meetings, every member could then decide which task he will become responsible of. Even if there is only one responsible per task, it's the whole team who has the global responsibility to reach the sprint goal. Therefore there may be more than one person working on a task.
The estimations are done in hours for the tasks, which are smaller than the user stories they belong, and therefore more precise.
In the Burndown chart, which shows the number of remaining hours, the red and blue lines have to start at the same position, as at the beginning of the first day of the sprint the theoretical and real number of hours are the same.
Examples des tâches
Prepare the work environment Understanding requirement Documentation Research Android/Java Mockups Thinking Mockups and prototypes desingning Create the Product Backlog Meeting with PO Create one simple table in the DB Service code to retrieve data from DB Display on Android Screen
Sprint 0 description
Un Sprint 0 pour préparer l’environnement de travail :
- préparer l’équipe et le cadre technique
- créer les fondations du projet
- constituer le Product Backlog initial

## Sprint 1
|  |  | Sprint | 1
| User stories |  | Start date | 2025-12-11
| 1. DB Development |  | End date (included) | 2025-12-17
| 8.1 Finishing the first DB version structure |  | Sprint goal | Prepare all the environment to be ready to develop the project
| 8.2 Creating all Tables |  | Nbre working days | 5
15 Testing all Tables , Links (FK) and Columns
14 Feed data base with mockup data
13 DB stored procedure and indexing
| 2. Design and prototyping |  | Create the Product Backlog |  | TRAVAIL RESTANT A FAIRE - PAS TRAVAIL DEJA EFFECTUE
11 Final mockups and prototypes desingning
10 Create the Product Backlog (was rejected)
3. Planning and Coordination
12.1 Planification of taks and holidays work planning
12.2 Contact with PO
9 Research and final choice of the technological stack
[5 empty] | Day 01 | Day 02 | Day 03 | Day 04 | Day 05
ID US.task | Task Name | Resp. | Initial Estimate |  | 2025-12-11 | 2025-12-12 | 2025-12-15 | 2025-12-16 | 2025-12-17
8.1 | Finishing the first DB version structure | Gaëtan | 8 |  | 8 | 6 | 4 | 2 | 0
8.2 | Creating all Tables | Vadym | 10 |  | 10 | 9 | 6 | 2 | 0
9 | Research and final choice of the technological stack | Gaëtan | 3 |  | 3 | 1 | 1 | 0 | 0
10 | Create the Product Backlog (was rejected) | Gaëtan | 4 |  | 4 | 3 | 1 | 1 | 0
11 | Mockups and prototypes desingning final | Vadym | 6 |  | 6 | 1 | 1 | 1 | 0
12.1 | Planification of taks and holidays work planning | Everyone | 2 |  | 2 | 2 | 2 | 2 | 0
12.2 | Contact with PO | Everyone | 1 |  | 1 | 1 | 1 | 1 | 0
13 | DB stored procedure and indexing | Everyone | 5 |  | 5 | 4 | 3 | 2 | 0
14 | Feed data base with mockup data | Gaëtan | 1 |  | 1 | 1 | 1 | 1 | 0
15 | Testing all Tables , Links (FK) and Columns | Everyone | 1 |  | 1 | 1 | 1 | 1 | 0
|  | Total | 41
|  | Remaining | 41 |  | 41 | 29 | 21 | 13 | 0
|  | Theoretical |  |  | 41 | 30.75 | 20.5 | 10.25 | 0
Note on E5: Modify the table below and Burndown chart according to the number of working days
Note on F16: The first day of the sprint you start at 8 o'clock therefore the remaining effort is the same as the initial estimate
Note on D17: Author: This is the team's initial assessment of how much work is needed to implement this task. The unit is hours. This part must be filled by developers only. Not by the product owner
Note on F17: The first day of the sprint you start at 8 o'clock therefore the remaining effort is the same as the initial estimate
Note on D29: Author: Initial total of Scrum units

## Sprint 2
|  |  | Sprint | 2
| User stories |  | Start date | 2025-12-18
| 1. Infrastructure & Setup |  | End date (included) | 2025-12-24
| 17.1 Server Django creation |  | Sprint goal | Prepare all the environment to be ready to develop the project
| 17.2 Connection DB and entity creation |  | Nbre working days | 5
2. Backend Development
| 18.1 Implements Python Backend |  | Create the Product Backlog |  | TRAVAIL RESTANT A FAIRE - PAS TRAVAIL DEJA EFFECTUE
18.2 Add shared functions and views between users
18.3 Add specific functions and views for each role
3. Core Features
19.1 Issue submission
19.2 Issue lifecycle
19.3 Role-Based visibility
4. Testing & Validation
16 Team technological compatibility check
20.1 Add minimum PO's requirements
20.2 Alpha-Test
20.3 Beta-Test
[5 empty] | Day 01 | Day 02 | Day 03 | Day 04 | Day 05
ID US.task | Task Name | Resp. | Initial Estimate |  | 2025-12-18 | 2025-12-19 | 2025-12-22 | 2025-12-23 | 2025-12-24
16 | Team technological compatibility check | Vadym | 1 |  | 1 | 0 | 0 | 0 | 0
17.1 | Server Django creation | Gaëtan | 4 |  | 4 | 0 | 0 | 0 | 0
17.2 | Connection DB and entity creation | Vadym | 6 |  | 6 | 4 | 2 | 0 | 0
18.1 | Implements Python Backend | Gaëtan | 8 |  | 8 | 6 | 4 | 2 | 0
18.2 | Add shared functions and views between users | Gaëtan | 4 |  | 4 | 4 | 4 | 2 | 0
18.3 | Add specific functions and views for each role | Vadym | 2 |  | 2 | 2 | 1 | 0 | 0
19.1 | Issue submission | Gaëtan | 4 |  | 4 | 2 | 0 | 0 | 0
19.2 | Issue lifecycle | Vadym | 2 |  | 2 | 1 | 0 | 0 | 0
19.3 | Role-Based visibility | Vadym | 4 |  | 4 | 3 | 2 | 1 | 0
20.1 | Add minimum PO's requirements | Gaëtan | 2 |  | 2 | 2 | 2 | 1 | 0
20.2 | Alpha-Test | Everyone | 4 |  | 4 | 4 | 4 | 0 | 0
20.3 | Beta-Test | Everyone | 2 |  | 2 | 2 | 2 | 1 | 0
|  | Total | 42
|  | Remaining | 42 |  | 42 | 30 | 21 | 7 | 0
|  | Theoretical |  |  | 42 | 31.5 | 21 | 10.5 | 0
Note on E5: Modify the table below and Burndown chart according to the number of working days
Note on F19: The first day of the sprint you start at 8 o'clock therefore the remaining effort is the same as the initial estimate
Note on D20: Author: This is the team's initial assessment of how much work is needed to implement this task. The unit is hours. This part must be filled by developers only. Not by the product owner
Note on F20: The first day of the sprint you start at 8 o'clock therefore the remaining effort is the same as the initial estimate
Note on D34: Author: Initial total of Scrum units

## Sprint 3
|  |  | Sprint | 3
| User stories |  | Start date | 2025-12-25
| 1. Requirements |  | End date (included) | 2026-01-03
| 21 Add additional PO's requirements |  | Sprint goal | Prepare all the environment to be ready to develop the project
| 2. Frontend Development |  | Nbre working days | 6
22.1 Implement Frontend Web Django Interface (design)
| 22.2 Implement Frontend Web Django Interface (code-interface) |  | Create the Product Backlog |  | TRAVAIL RESTANT A FAIRE - PAS TRAVAIL DEJA EFFECTUE
23 Implement link between Frontend and Backend
3. Core Features
24.1 Simple messaging system
24.2 Upload photos for tickets
25 Reassignment
26.1 SLA awareness
26.2 Extended status model and their visualization
[5 empty] | Day 01 | Day 02 | Day 03 | Day 04 | Day 05 | Day 06
ID US.task | Task Name | Resp. | Initial Estimate |  | 2025-12-25 | 2025-12-26 | 2025-12-29 | 2025-12-30 | 2026-01-02 | 2026-01-03
21 | Add additional PO's requirements | Vadym | 2 |  | 2 | 0 | 0 | 0 | 0 | 0
22.1 | Implement Frontend Web Django Interface (design) | Vadym | 6 |  | 6 | 6 | 6 | 3 | 0 | 0
22.2 | Implement Frontend Web Django Interface (code-interface) | Everyone | 10 |  | 10 | 4 | 0 | 0 | 0 | 0
23 | Implement link between Frontend and Backend | Gaëtan | 8 |  | 8 | 6 | 4 | 2 | 0 | 0
24.1 | Simple messaging system | Vadym | 6 |  | 6 | 6 | 6 | 4 | 2 | 0
24.2 | Upload photos for tickets | Gaëtan | 4 |  | 4 | 4 | 4 | 4 | 2 | 0
25 | Reassignment | Everyone | 8 |  | 8 | 8 | 0 | 0 | 0 | 0
26.1 | SLA awareness | Gaëtan | 2 |  | 2 | 2 | 2 | 2 | 0 | 0
26.2 | Extended status model and their visualization | Gaëtan | 2 |  | 2 | 2 | 2 | 2 | 0 | 0
|  | Total | 48
|  | Remaining | 48 |  | 48 | 38 | 24 | 17 | 4 | 0
|  | Theoretical |  |  | 48 | 38.4 | 28.8 | 19.2 | 9.6 | 0
Note on E5: Modify the table below and Burndown chart according to the number of working days
Note on F15: The first day of the sprint you start at 8 o'clock therefore the remaining effort is the same as the initial estimate
Note on D16: Author: This is the team's initial assessment of how much work is needed to implement this task. The unit is hours. This part must be filled by developers only. Not by the product owner
Note on F16: The first day of the sprint you start at 8 o'clock therefore the remaining effort is the same as the initial estimate
Note on D27: Author: Initial total of Scrum units

## Sprint 4
|  |  | Sprint | 4
| User stories |  | Start date | 2026-01-05
| 27.1 Check Security and corrections |  | End date (included) | 2026-01-14
| 27.2 Final application testing |  | Sprint goal | Prepare all the environment to be ready to develop the project
| 28 Final check with the client |  | Nbre working days | 11
29 Presentation preparation
|  |  | Create the Product Backlog |  | TRAVAIL RESTANT A FAIRE - PAS TRAVAIL DEJA EFFECTUE
[5 empty] | Day 01 | Day 02 | Day 03 | Day 04 | Day 05 | Day 06 | Day 07 | Day 08 | Day 09 | Day 10
ID US.task | Task Name | Resp. | Initial Estimate |  | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14
27.1 | Check Security and corrections | Everyone | 2 |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27.2 | Final application testing | Everyone | 12 |  | 12 | 12 | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0
28 | Final check with the client | Everyone | 1 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Presentation preparation | Everyone | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Total | 16
|  | Remaining | 16 |  | 16 | 16 | 13 | 11 | 9 | 7 | 5 | 3 | 1 | 0
|  | Theoretical |  |  | 16 | 14.4 | 12.8 | 11.2 | 9.6 | 8 | 6.4 | 4.8 | 3.2 | 1.6
Note on E5: Modify the table below and Burndown chart according to the number of working days
Note on F8: The first day of the sprint you start at 8 o'clock therefore the remaining effort is the same as the initial estimate
Note on D9: Author: This is the team's initial assessment of how much work is needed to implement this task. The unit is hours. This part must be filled by developers only. Not by the product owner
Note on F9: The first day of the sprint you start at 8 o'clock therefore the remaining effort is the same as the initial estimate
Note on D15: Author: Initial total of Scrum units

## Done Definition
DONE DEFINITION FOR ALL USER STORIES
A User Story is considered DONE when all the following criteria are met:
1. Functional Requirements
| The User Story fully meets the described functional needs | DONE?
| All Acceptance Criteria are implemented and validated | DONE?
| No known blocking or critical bugs remain | DONE?
| Identified edge cases have been handled | DONE?
2. Code Quality
| Code is fully implemented, clean, and well-structured | DONE?
| Coding standards and naming conventions are respected | DONE?
| Code is commented where necessary | DONE?
| No blocking errors or warnings remain | DONE?
3. Testing
| Unit tests are written and executed | DONE?
| All tests pass successfully | DONE?
| Main and alternative scenarios are tested | DONE?
| Tests have been reviewed or validated by a team member | DONE?
4. Version Control & Integration
Code is committed to the version control system (Git)
Commit messages are clear and meaningful
Code is merged without conflicts
The main branch remains stable and functional
5. Documentation
| The feature is documented in the code | DONE?
| User documentation or README is updated | DONE?
| Important technical choices are explained if necessary | DONE?
6. Validation & Review
| The feature is deployable and demonstrable | DONE?
| The User Story has been reviewed and validated by the team | DONE?
| The User Story can be presented during the sprint review | DONE?
Information:
The definition of done tab contains an evolutive list of tasks that the team has to perform after completing each user story, in order to maximize the global quality of the code and his work.

## Retroperspective
SPRINT 0 | End : 10.12.2025
Name | What went Good ? | What went Wrong ? | How to improve ?
Gaëtan | Experienced in Data Analysis, expert in Excel | Unclear acceptance criteria initially | Cut vertical slices thinner to avoid hidden dependencies
Jonathan | Experienced in project management and global client vision | Limited availability due to other commitments | Share about "blockers" earlier
Vadym | Brought fresh ideals | Hidden difficulties that were not noticed during the initial review of the project | Validate specific requirements with the product owner
Everyone | Internal communication stayed tight because the team worked from one shared board | It was difficult to start the project because we couldn't come to an agreement | Limit features to minimum for the first sprint
SPRINT 1 | End : 17.12.2025
Name | What went Good ? | What went Wrong ? | How to improve ?
Gaëtan | Was able to finish DB just in time | Worked alone on DB | Try pair programming or core review
Vadym | All work proceeds according to graphic | Some tasks dependend on others | Identify dependencies during sprint
Everyone |  | Team dynamics | Disband team
SPRINT 2 | End : 24.12.2025
Name | What went Good ? | What went Wrong ? | How to improve ?
Gaëtan | Flexibility when facing unexpected issues | Some things slipped through | Use a checklist
Vadym | Shared uselful tips and tricks | Was blocked with designated task | Ask for help earlier
Everyone | Were able to adapt to the new requirements Decisions made quickly | Stress due to tight deadlines | Better planning during holidays
SPRINT 3 | End : 03.01.2026
Name | What went Good ? | What went Wrong ? | How to improve ?
Gaëtan | Good knowledge sharing between members | Took too much work | Underestimated task complexity
Vadym | Always available when needed | Took time to adapt to new tools | Schedule quick onboarding sessions
Everyone | Constructive feedback between us No blame culture | During holidays live meetings became less frequent | Become comfortable using online communication tools
SPRINT 4 | End : 14.01.2026
Name | What went Good ? | What went Wrong ? | How to improve ?
Gaëtan | Consistent quality of work | Not enough time to finish all additional tasks | Focus on principal objectives
Vadym | Completed all assigned tasks | Focused on details, lost big picture | Step back and review goals regularly
Everyone | Felt comfortable sharing ideas | General fatigue (end of semester) | Take turns on critical tasks
General feedback / Sprint Review
- Keep it simple / Don't waste time on unimportant things
- Sort orders by date and time - History by delete an order / Rename deletebutton -> cancel - Demo: Better to explain a US then demo, then the next US and the demo and so on - In the next sprint the rider should be in focus / The app should be seen as the rider's point of view
- Good that the whole concept (welcomepage) has already been implemented, because so you can see how it will look at the end
General feedback / Sprint Review
- good Demo / Presentation
- Handling with the checkpoints is nice
- In the next sprint, the accountant should be In focus / clean all bugs
-When logging in to Google, the password should always be requested when logging in, i.e. do not save the password.
-We will receive a list with all important attributes for the accountant from the PO.
-On the LoginPage the fields e-mail address and password should not be filled in automatically.
-It was good that we had published a current version in the store. Update it from time to time.
Information
The retrospective tab contains the summary of the discussions of the team during the retrospective event, at the end of every sprint. Everyone should speak and answer the questions: What went good? What went wrong? What should be improved?

## DailyMeeting
Sprint | When | Who | What did you do since last time? | What will you work on today? | Do you have any obstacles?
0 | 2.12.2025 | Everyone | Start of the project | Identify roles | Different views on the project
|  | Gaëtan |  | Prepare the work environment
|  | Vadym |  | Understanding requirement + Vision
0 | 5.12.2025 | Gaëtan | Enviroment is ready to be used + DataGrip integration | DB modeling + DB mockup
|  | Everyone | Identified main roles and actors for the project | Mockups and prototypes desingning
|  | Vadym | Centralized description for the project, including the general vision | Product Backlog
0 | 10.12.2025 | Gaëtan | DB mockup finalised | Continued work on DB
|  | Vadym | Product backlog created | Understanding requirement + Vision
|  | Everyone |  |  | Communication problems
1 | 11.12.2025 | Gaëtan | Sprint 0 completed | Finishing the first DB version structure (US#11)
|  | Vadym | Sprint 0 completed | Mockups and prototypes designing final (US#14)
|  | Gaëtan | Sprint 0 completed | Research and final choice of technological stack (US#12)
1 | 13.12.2025 | Gaëtan | DB structure 50% done | Continue DB structure (US#11)
|  | Gaëtan | Final mockups in progress | Create the Product Backlog update (US#13)
|  | Everyone | Tech stack chosen (Django + PostgreSQL) | Planification of tasks and holidays (US#15)
1 | 16.12.2025 | Everyone | Task, project reflection and projection | Finishing the Backlogs, excel sheets and project tasks planification (US#13, #15)
|  | Gaëtan | Technological research | Technological choices agreement (US#12)
|  | Gaëtan | Finish DB | Polishing and creating views and queries (US#17)
|  | Everyone | DB and views final version prototype | DB Validation
1 | 17.12.2025 | Everyone | Testing | Finish Excel for Sprint 1
|  | Vadym | Planning and coordination | Creating all Tables (US#16)
|  | Gaëtan | Filled DB with mockup data (US#18) | Testing all Tables, Links, Columns (US#19)
2 | 18.12.2025 | Gaëtan | Sprint 1 completed, DB ready | Server Django creation (US#21)
|  | Vadym | Sprint 1 completed | Team technological compatibility check (US#20)
|  | Vadym | Sprint 1 completed | Connection DB and entity creation (US#22)
2 | 20.12.2025 | Gaëtan | Django server running | Implements Python Backend (US#23)
|  | Gaëtan | Tech check done, all good | Add minimum PO's requirements (US#25) | Waiting for PO confirmation
|  | Vadym | ORM entities created | Add shared functions and views (US#26)
2 | 22.12.2025 | Gaëtan | Backend views and logic in progress | Continue Python Backend (US#23) | Holiday availability reduced
|  | Vadym | PO requirements added | Add specific functions per role (US#27)
|  | Gaëtan | Shared functions done (login, dashboard) | Issue submission (US#28)
2 | 24.12.2025 | Everyone | Backend logic done | Alpha-Test (US#24)
|  | Vadym | Role-specific functions done | Issue lifecycle (US#29)
|  | Vadym | Issue submission working | Role-Based visibility (US#30)
|  | Everyone |  | Beta-Test (US#31) | Holiday break starting
3 | 27.12.2025 | Everyone | Beta-test completed | Implement Frontend Web Django Interface - design (US#33)
|  | Vadym | Sprint 2 review done | Add additional PO's requirements (US#32)
|  | Everyone | Role-based visibility done | Implement Frontend Web Django Interface - code (US#34)
3 | 30.12.2025 | Vadym | Frontend design in progress | Continue frontend design (US#33)
|  | Gaëtan | PO requirements updated | Implement link between Frontend and Backend (US#35)
|  | Vadym | Frontend code started | Simple messaging system (US#36)
3 | 02.01.2026 | Gaëtan | Frontend design done | Upload photos for tickets (US#37)
|  | Everyone | Frontend-Backend linked | Reassignment feature (US#38) | Low priority, might skip
|  | Gaëtan | Messaging system working | SLA awareness (US#39)
3 | 03.01.2026 | Gaëtan | Photo upload done | Extended status model (US#40)
|  | Everyone | Reassignment done | Sprint 3 review prep
|  | Gaëtan | SLA levels implemented | Sprint 3 review prep
4 | 06.01.2026 | Gaëtan | Sprint 3 completed | Check Security and corrections (US#41)
|  | Everyone | Sprint 3 completed | Final check with the client (US#43)
|  | Vadym | Sprint 3 completed | Final application testing (US#42)
4 | 08.01.2026 | Gaëtan | Security check done | Presentation preparation (US#44)
|  | Everyone | Client feedback received | Presentation preparation (US#44)
|  | Vadym | Final testing done, no critical bugs | Presentation preparation (US#44)
4 | 10.01.2026 | (Everyone) | Presentation ready | Final demo to client
Information:
The Daily Meeting tab should contain the answers to the three questions: What did I do since last time, what will I do today, and, Did I meet any problems in my tasks. This meeting should last maximum 15 min every full day of work.

## Student1 Journal
Name | Date | What | Time | Type | Total hours
| 2023-09-23 | Meeting avec les Product Owner et le Coach | 2:00 | Meeting | 17:00 | The goal of this journal is that each student writes the work done with its respective time spent.
| 2023-09-23 | Installation outils et composants requis | 2:00 | Preparation |  | This formally not asked by SCRUM, but useful to monitor the work of each student in the team.
| 2023-09-23 | Clone des projets Git fournis par les Product Owner | 2:00 | Preparation |  | Here are some example lines of the journal to illustrate it.
| 2023-09-30 | Daily Meeting | 0:30 | Meeting
| 2023-09-30 | Récupération du projet de base et tenter de le faire fonctionner | 2:00 | Preparation
| 2023-10-01 | Ajout du networking au projet avec un script pour tester | 2:00 | Dev
| 2023-10-07 | Daily Meeting + planning poker | 1:30 | Meeting
| 2023-10-14 | Daily Meeting | 2:00 | Meeting
| 2023-10-14 | Possibilité de tester plusieurs joueurs ajout d'interface pour se connecter en server, host,... debuguer le problème | 3:00 | Dev
etc. etc. etc.
PO said journals are not required

## Student2 Journal
Name | Date | What | Time | Type | Total hours
| 2023-09-23 | Meeting avec les Product Owner et le Coach | 2:00 | Meeting | 17:00 | The goal of this journal is that each student writes the work done with its respective time spent.
| 2023-09-23 | Installation outils et composants requis | 2:00 | Preparation |  | This formally not asked by SCRUM, but useful to monitor the work of each student in the team.
| 2023-09-23 | Clone des projets Git fournis par les Product Owner | 2:00 | Preparation |  | Here are some example lines of the journal to illustrate it.
| 2023-09-30 | Daily Meeting | 0:30 | Meeting
| 2023-09-30 | Récupération du projet de base et tenter de le faire fonctionner | 2:00 | Preparation
| 2023-10-01 | Ajout du networking au projet avec un script pour tester | 2:00 | Dev
| 2023-10-07 | Daily Meeting + planning poker | 1:30 | Meeting
| 2023-10-14 | Daily Meeting | 2:00 | Meeting
| 2023-10-14 | Possibilité de tester plusieurs joueurs ajout d'interface pour se connecter en server, host,... debuguer le problème | 3:00 | Dev
etc. etc. etc.
PO said journals are not required